## By Date
Class Schedule Production Timeline - Spring 2022
Last Updated: 9/16/21 - jbm
Date |  | Responsibility | Activity
December 2017
2017-12-04 | Mon | Erica Marrone, Curriculum Analyst | Email CALT document to Schedule Preparers and request confirmation of dates
2017-12-18 | Mon | VPIs | Return CALT dates and parameters to Shelly Hess
2017-12-18 | Mon | Erica Marrone, Curriculum Analyst | Deliver CALT dates to Student Services
January 2018
2018-01-12 | Fri | Erica Marrone, Curriculum Analyst | Roll Spring 2018 to Spring 2021 in ISIS Scheduler Project Available for Input After the Roll
2018-01-15 | Mon | Student Services Analyst | Make Scheduler available (Melonie)
2018-01-15 | Mon | Department Chairs | Update Spring 2021 class information in ISIS/Scheduler
1/15 - 5/4 |  | Schedule Preparers | Update Spring 2020 class information in ISIS
2018-05-04 | Fri | Team of Schedule Preparers | Scheduler availability ends for Spring 2021
5/4 - 9/28 |  | Jeff Mills, Systems Support Analyst | Run B2511 and 2505 printers proofs for Spring 2021
5/4 - 9/28 |  | Team of Schedule Preparers | Use B2511 and B2505 printers proofs to enter Spring 2021 class data manually into Campus Solutions begins.
2018-06-08 | Fri | Schedule Preparers | END data entry for Spring 2021 class sections in ISIS
2018-06-19 | Tue | Schedule Preparers | Begin entering Spring 2021 class schedule data in Campus Solutions
2018-07-24 | Tue | IT Production Control? | Class Schedule Report available (replaces printers proofs)
2018-07-28 | Sat | Schedule Preparers | Last day for Spring 2020 class schedule data entry in Campus Solutions at Corporate Ed Center.
June 2021
2021-06-18 | Fri | Erica Marrone, Curriculum Analyst | ISIS Roll Forward Spring 2021 to Spring 2022
August 2021
2021-08-10 | Tue | Student Systems Analyst | Update Crosswalk Table X_ISCLASS_AE in CS Production environment
2021-08-11 | Wed | Student Systems Analyst | Deliver cover changes to District Graphic Artist
2021-08-11 | Wed | District Graphic Artist | Select photos for cover
2021-08-11 | Wed | Director, Communications and Public Relations | Review Chancellor's Welcome Message and provide updates to Multimedia Specialist
2021-08-16 | Mon | Dean, Workforce Development | Report any changes to Corporate Council logos to District Graphic Designer (Claudia)
2021-08-20 | Fri | Student Systems Support Technician | Deliver highlighted changes in MS Word (final narrative, academic calendars/common pages, fee information, policy statements, etc. for Combo class schedules) to Multimedia Specialist
2019-08-23 | Fri | Schedule Preparers | END data entry for Spring class sections in ISIS; all changes, updates, or additions to Spring 2020 schedule will be in Campus Solutions by the CS Schedule team 8/28/2018.
2018-08-24 | Fri | Systems Support Analyst and Schedule Preparers | Run Schedule Report from ISIS
2021-08-30 | Mon | Systems Support Analyst | First download of spring 2022 schedule in CS
2021-08-30 | Mon | Systems Support Analyst | Send ISCLASS listings to Schedule Preparers
2019-08-28 | Wed | Schedule Preparers | Schedulers start entering Spring 2020 class schedule data in Campus Solutions as a group
2018-08-13 | Mon | Jeff Mills, Systems Support Analyst | Run FDD 728 and email files to Schedule Preparers, Distance Ed Coordinators, and Bookstore Supervisor.
September 2021
2021-09-06 | Mon | Holiday - Labor Day
2021-09-10 | Fri | Honors Coordinators – Veronica Derace & Ian Duckles. | Deliver changes to District Honors page to Multimedia Specialist
2021-09-10 | Fri | Dean, Online Instruction and Distributed Learning | Deliver changes to online learning common page (page prior to course listings) to Multimedia Specialist
2021-09-10 | Fri | Continuing Education Graphic Artist | Deliver Continuing Education pages (in pdf format) to Multimedia Specialist
2021-09-10 | Fri | Publications Editor & Supervisor | Email Sun Distributing list to PIOs for review and update
2021-09-10 | Fri | Public Information Officers | Return review Sun Distributing list to Publications Editor & Supervisor
2021-09-15 | Wed | Multimedia Specialist | Compile common pages and International Ed/Honors ads (in InDesign format) in case needed for schedule pagination
2021-09-15 | Wed | District Graphic Artist | Present draft of updated cover to Director
October 2021
2021-10-01 | Fri | Schedule Preparers | Input last changes to class schedule in CS prior to download. No changes after 5:00 PM
2021-10-04 | Mon | Jeff Mills, Systems Support Analyst | Run ISCLASS run control in CS and email Schedule Preparers the listings
2021-10-04 | Mon | Eric Nunes, Multimedia Specialist | Email Military Ed listings and Online course listings to Schedule Preparers for review
2021-10-04 | Mon | Schedule Preparers | Print and distribute course listings. Coordinate review of CS content with department chairs and campus deans. Update content changes/corrections in CS. Report errors regarding title and short course descriptions to Instructional Services
2021-10-08 | Fri | Student Systems Support Technician | Reviews first draft of narrative (First Review)
2021-10-08 | Fri | Eric Nunes, Multimedia Specialist | Notify Student Services’ staff page proofs are available. Distribute, complete, and retain SDCCD class schedule proofing sign-off forms.
2021-10-11 | Mon | TBD by each College | Deliver Changes to Off-Campus locations to Multimedia Specialist (City-Jeanie Tyler; Mesa-Arlis Svedberg; Miramar-Melanie Cordero)
2021-10-14 | Thu | Student Systems Support Technician | First review changes due back to IS Multimedia Specialist (additional changes after this date may be made with SDCCD class schedule proofing sign-off form)
2021-10-15 | Fri | Schedule Preparers | Input final corrections to class schedule prior to final download. No changes after 5:00 PM. This is the final input deadline for CS data to be included in printed schedule. Any changes after 5pm will be reflected in online schedule, but not printed schedule1
2021-10-18 | Mon | Eric Nunes, Multimedia Specialist | Email updated Military Ed page to Schedule Preparers and Director, Off-Campus Programs (Catherine Shafer).
2021-10-18 | Mon | Schedule Preparers | FINAL download for the printed Class Schedule from Campus Solutions
2021-10-04 | Mon | Susan Topham, Vice Chancellor, Educational Services | Drop dead date to cancel printed schedule production
2021-10-18 | Mon | Jeff Mills, Systems Support Analyst | Email course listings to Schedule Preparers, Distance Ed Coordinators, and Bookstore Supervisor
2021-10-18 | Mon | Schedule Preparers | Begin final formatting of course listings in MS Word
2021-10-18 | Mon | Schedule Preparers | Colleges review class listings and make corrections in Campus Solutions
2021-10-18 | Mon | Student Systems Support Technician | Post class schedule to the web. CS Online Class Schedule available to the public.
2021-10-21 | Thu | District Graphic Artist | Final cover art due. Beresford/Chancellor signoff
2021-10-21 | Thu | Multimedia Specialist | Integrate changes to online listings from all three colleges into InDesign
2021-10-25 | Mon | Schedule Preparers | Deliver MS Word formatted course listings to PIOs (1st proof)
2021-10-25 | Mon | Schedule Preparers, Director of Off-Campus Programs | Email corrections to Military Ed page to Multimedia Specialist
2021-10-25 | Mon | Schedule Preparers | Add comments to online course listings file, make corrections/changes, and email file to Multimedia Specialist
2021-10-26 | Tue | Information Officers | Return MS Word formatted course listings to Schedule Preparers (1st proof)
2021-10-28 | Thu | Multimedia Specialist | Email online course listings PDF to Schedule Preparers for review
2021-10-29 | Fri | Jeff Mills, Systems Support Analyst | Download ISCLASS section comments for review. Send to Dean, Curriculum Services and Curriculum Technician for review
November 2021
2021-11-01 | Mon | Information Officers | Deliver proofs to Schedule Preparers/VP Instruction-final review
2021-11-02 | Tue | Schedule Preparers | Return corrected page proofs to PIOs in AM, return online listings PDF with any changes to Multimedia Specialist
2021-11-02 | Tue | Jeff Mills, Systems Support Analyst | Send section comments to Dean, Instructional Services and Curriculum Technician for review
2021-11-09 | Tue | Information Officers / VP’s Instruction | Deliver campus pages in hard copy and InDesign digital file to Jeff Mills, Systems Support Analyst in the AM
2021-11-09 | Tue | Multimedia Specialist | Compiles sections of the combo and repaginates
2021-11-10 | Wed | Vice Presidents of Student Services | Email campus quantities needed to Jeff Mills, Systems Support Analyst.
2021-11-10 | Wed | Mail Room Clerk | Prepare Postal Form for mailing combo schedules
2021-11-11 | Thu | Holiday - Veterans Day
2021-11-15 | Mon | Multimedia Specialist | Notify campus Information Officers and Student Services’ staff page proofs are available. Distribute, complete, and retain SDCCD class schedule proofing sign-off forms.
2021-11-15 | Mon | Student Systems Support Technician/Information Officers/Multimedia Specialist | Proof combo digital page proofs in Instructional Services-check calendars, narrative, and legal information specifically. Distribute, complete, and retain SDCCD sign-off forms. Update In Design files with help from System Support Analyst (Final Proof--All changes must be made by 5:00 pm)
2021-11-18 | Thu | Jeff Mills, Systems Support Analyst | Upload page proofs to printers. Printer build plates and creates bluelines.
2021-11-19 | Fri | Commercial Printer (Advantage, Inc.) | Printer converts page proofs to bluelines and emails them to Systems Support Analyst
2021-11-22 | Mon | Student Systems Support Technician/Information Officers/Multimedia Specialist | Sys Support Analyst and Multimedia specialist provide reviewers with bluelines for final proofing.
2021-11-24 | Wed | Jeff Mills, Systems Support Analyst | Upload combo blueliness, cover art, to Advantage, Inc.
2021-11-24 | Wed | Shelly Hess, Dean, Curriculum Services | Send section comments corrections to Schedule Preparers to update CS
2021-11-25 | Thu | Holiday - Thanks Giving
December 2021
2021-12-02 | Thu | Advantage, Inc. | Deliver combo schedules to District sites and Post Office, and minimum of 600 combo schedules to Student Services 2
2021-12-06 | Mon | Student Services | Open Registration Starts
2022-02-04 | Fri | Jeff Mills, Systems Support Analyst | Contact Warehouse to recycle remaining schedules
Educational Services Division, District Office
| Vice Chancellor, Educational Services |  | Susan Topham
| Acting Dean, Educational Support Services |  | Krystal Henderson
| Dean, Online Instruction & Learning |  | Brian Weston
| Dean, Career Educaton & Workforce Development |  | Amertah Perman
| Dean, Instructional Services |  | Shelly Hess
| Systems Support Analyst, Educational Support Services |  | Jeff Mills
| Student Systems Support Technician, Student Services |  | Danya Sanchez
| Multimedia Specialist, Instructional Services |  | Eric Nunes
| Curriculum Analyst, Instructional Services |  | Erica Marrone
| Curriculum Technician, Instructional Services |  | Trila Gil
Communications and Public Relations, District Office
| District Graphic Artist |  | Claudia Azcona-Mercado
| Publications Editor & Supervisor |  | Leslie Hackett
District Sites (Colleges and CE Campuses)
| IT Production Control |  | District/Miramar
| Information Officers (PIOs) |  | Cesar Gumapas (City)
Jennifer Kearns (Mesa)
Stephen Quis (Miramar)
Ranessa Ashton (Continuing Education)
| Graphic Artists |  | Kim La Rue (City)
Hai Duong (Mesa)
Joan Mize (Miramar)
Luisa Davila (Continuing Education)
| Schedule Preparers |  | Kamini Bhakta (City)
Arlis Svedberg (Mesa)
Jennifer Ock and Melanie Cordero (Miramar)
Honors Coordinators
| District |  | Carmen Jay and Kirk Webley (Miramar)
| City |  | Kelly Mayhew and Hector Martinez
| Mesa |  | Ranmali Rodrigo and Rosiangela Escamilla
Off-site Printers
| Advantage, Inc. |  | Chris Baker, Mary Lytch
¹Production staff (i.e. district and non-district personnel involved in producing class schedules) will not be held accountable for meeting production timelines for information or alterations to the schedule, which are submitted after 5:00 PM on this date.
²We attempt to arrange schedule delivery by 10:00 AM and pick up by 2:00 PM; however this is subject to change depending on conditions at the time. Please contact Educational Services for more information.

## By Responsibility
Date |  | Responsibility | Activity
December 2017
2017-12-04 | Mon | Erica Marrone, Curriculum Analyst | Email CALT document to Schedule Preparers and request confirmation of dates
2017-12-18 | Mon | VPIs | Return CALT dates and parameters to Shelly Hess
2017-12-18 | Mon | Erica Marrone, Curriculum Analyst | Deliver CALT dates to Student Services
January 2018
2018-01-12 | Fri | Erica Marrone, Curriculum Analyst | Roll Spring 2018 to Spring 2021 in ISIS Scheduler Project Available for Input After the Roll
2018-01-15 | Mon | Student Services Analyst | Make Scheduler available (Melonie)
2018-01-15 | Mon | Department Chairs | Update Spring 2021 class information in ISIS/Scheduler
1/15 - 5/4 |  | Schedule Preparers | Update Spring 2020 class information in ISIS
2018-05-04 | Fri | Team of Schedule Preparers | Scheduler availability ends for Spring 2021
5/4 - 9/28 |  | Jeff Mills, Systems Support Analyst | Run B2511 and 2505 printers proofs for Spring 2021
5/4 - 9/28 |  | Team of Schedule Preparers | Use B2511 and B2505 printers proofs to enter Spring 2021 class data manually into Campus Solutions begins.
2018-06-08 | Fri | Schedule Preparers | END data entry for Spring 2021 class sections in ISIS
2018-06-19 | Tue | Schedule Preparers | Begin entering Spring 2021 class schedule data in Campus Solutions
2018-07-24 | Tue | IT Production Control? | Class Schedule Report available (replaces printers proofs)
2018-07-28 | Sat | Schedule Preparers | Last day for Spring 2020 class schedule data entry in Campus Solutions at Corporate Ed Center.
2021-12-02 | Thu | Advantage, Inc. | Deliver combo schedules to District sites and Post Office, and minimum of 600 combo schedules to Student Services 2
2021-11-19 | Fri | Commercial Printer (Advantage, Inc.) | Printer converts page proofs to bluelines and emails them to Systems Support Analyst
2021-09-10 | Fri | Continuing Education Graphic Artist | Deliver Continuing Education pages (in pdf format) to Multimedia Specialist
2021-09-10 | Fri | Dean, Online Instruction and Distributed Learning | Deliver changes to online learning common page (page prior to course listings) to Multimedia Specialist
2021-08-16 | Mon | Dean, Workforce Development | Report any changes to Corporate Council logos to District Graphic Designer (Claudia)
2021-08-11 | Wed | Director, Communications and Public Relations | Review Chancellor's Welcome Message and provide updates to Multimedia Specialist
2021-08-11 | Wed | District Graphic Artist | Select photos for cover
2021-09-15 | Wed | District Graphic Artist | Present draft of updated cover to Director
2021-10-21 | Thu | District Graphic Artist | Final cover art due. Beresford/Chancellor signoff
2021-10-04 | Mon | Eric Nunes, Multimedia Specialist | Email Military Ed listings and Online course listings to Schedule Preparers for review
2021-10-08 | Fri | Eric Nunes, Multimedia Specialist | Notify Student Services’ staff page proofs are available. Distribute, complete, and retain SDCCD class schedule proofing sign-off forms.
2021-10-18 | Mon | Eric Nunes, Multimedia Specialist | Email updated Military Ed page to Schedule Preparers and Director, Off-Campus Programs (Catherine Shafer).
2021-06-18 | Fri | Erica Marrone, Curriculum Analyst | ISIS Roll Forward Spring 2021 to Spring 2022
2021-09-06 | Mon | Holiday - Labor Day
2021-11-25 | Thu | Holiday - Thanks Giving
2021-11-11 | Thu | Holiday - Veterans Day
2021-09-10 | Fri | Honors Coordinators – Veronica Derace & Ian Duckles. | Deliver changes to District Honors page to Multimedia Specialist
2021-10-26 | Tue | Information Officers | Return MS Word formatted course listings to Schedule Preparers (1st proof)
2021-08-30 | Mon | Systems Support Analyst | First download of spring 2022 schedule in CS
2021-11-01 | Mon | Information Officers | Deliver proofs to Schedule Preparers/VP Instruction-final review
2021-11-09 | Tue | Information Officers / VP’s Instruction | Deliver campus pages in hard copy and InDesign digital file to Jeff Mills, Systems Support Analyst in the AM
2021-10-04 | Mon | Jeff Mills, Systems Support Analyst | Run ISCLASS run control in CS and email Schedule Preparers the listings
2021-10-18 | Mon | Jeff Mills, Systems Support Analyst | Email course listings to Schedule Preparers, Distance Ed Coordinators, and Bookstore Supervisor
2018-08-13 | Mon | Jeff Mills, Systems Support Analyst | Run FDD 728 and email files to Schedule Preparers, Distance Ed Coordinators, and Bookstore Supervisor.
2021-10-29 | Fri | Jeff Mills, Systems Support Analyst | Download ISCLASS section comments for review. Send to Dean, Curriculum Services and Curriculum Technician for review
September 2021
2021-11-02 | Tue | Jeff Mills, Systems Support Analyst | Send section comments to Dean, Instructional Services and Curriculum Technician for review
2021-11-18 | Thu | Jeff Mills, Systems Support Analyst | Upload page proofs to printers. Printer build plates and creates bluelines.
2021-11-24 | Wed | Jeff Mills, Systems Support Analyst | Upload combo blueliness, cover art, to Advantage, Inc.
2022-02-04 | Fri | Jeff Mills, Systems Support Analyst | Contact Warehouse to recycle remaining schedules
2021-11-10 | Wed | Mail Room Clerk | Prepare Postal Form for mailing combo schedules
2021-09-15 | Wed | Multimedia Specialist | Compile common pages and International Ed/Honors ads (in InDesign format) in case needed for schedule pagination
2021-10-21 | Thu | Multimedia Specialist | Integrate changes to online listings from all three colleges into InDesign
2021-10-28 | Thu | Multimedia Specialist | Email online course listings PDF to Schedule Preparers for review
2021-11-09 | Tue | Multimedia Specialist | Compiles sections of the combo and repaginates
2021-11-15 | Mon | Multimedia Specialist | Notify campus Information Officers and Student Services’ staff page proofs are available. Distribute, complete, and retain SDCCD class schedule proofing sign-off forms.
2021-09-10 | Fri | Public Information Officers | Return review Sun Distributing list to Publications Editor & Supervisor
2021-09-10 | Fri | Publications Editor & Supervisor | Email Sun Distributing list to PIOs for review and update
2019-08-23 | Fri | Schedule Preparers | END data entry for Spring class sections in ISIS; all changes, updates, or additions to Spring 2020 schedule will be in Campus Solutions by the CS Schedule team 8/28/2018.
2019-08-28 | Wed | Schedule Preparers | Schedulers start entering Spring 2020 class schedule data in Campus Solutions as a group
2021-10-01 | Fri | Schedule Preparers | Input last changes to class schedule in CS prior to download. No changes after 5:00 PM
2021-10-04 | Mon | Schedule Preparers | Print and distribute course listings. Coordinate review of CS content with department chairs and campus deans. Update content changes/corrections in CS. Report errors regarding title and short course descriptions to Instructional Services
2021-10-15 | Fri | Schedule Preparers | Input final corrections to class schedule prior to final download. No changes after 5:00 PM. This is the final input deadline for CS data to be included in printed schedule. Any changes after 5pm will be reflected in online schedule, but not printed schedule1
2021-10-18 | Mon | Schedule Preparers | FINAL download for the printed Class Schedule from Campus Solutions
2021-10-18 | Mon | Schedule Preparers | Begin final formatting of course listings in MS Word
2021-10-18 | Mon | Schedule Preparers | Colleges review class listings and make corrections in Campus Solutions
2021-10-25 | Mon | Schedule Preparers | Deliver MS Word formatted course listings to PIOs (1st proof)
2021-10-25 | Mon | Schedule Preparers | Add comments to online course listings file, make corrections/changes, and email file to Multimedia Specialist
2021-11-02 | Tue | Schedule Preparers | Return corrected page proofs to PIOs in AM, return online listings PDF with any changes to Multimedia Specialist
2021-10-25 | Mon | Schedule Preparers, Director of Off-Campus Programs | Email corrections to Military Ed page to Multimedia Specialist
2021-11-24 | Wed | Shelly Hess, Dean, Curriculum Services | Send section comments corrections to Schedule Preparers to update CS
2021-10-08 | Fri | Student Systems Support Technician | Reviews first draft of narrative (First Review)
2021-12-06 | Mon | Student Services | Open Registration Starts
2021-08-10 | Tue | Student Systems Analyst | Update Crosswalk Table X_ISCLASS_AE in CS Production environment
2021-08-11 | Wed | Student Systems Analyst | Deliver cover changes to District Graphic Artist
2021-08-20 | Fri | Student Systems Support Technician | Deliver highlighted changes in MS Word (final narrative, academic calendars/common pages, fee information, policy statements, etc. for Combo class schedules) to Multimedia Specialist
2021-10-14 | Thu | Student Systems Support Technician | First review changes due back to IS Multimedia Specialist (additional changes after this date may be made with SDCCD class schedule proofing sign-off form)
2021-10-18 | Mon | Student Systems Support Technician | Post class schedule to the web. CS Online Class Schedule available to the public.
2021-11-15 | Mon | Student Systems Support Technician/Information Officers/Multimedia Specialist | Proof combo digital page proofs in Instructional Services-check calendars, narrative, and legal information specifically. Distribute, complete, and retain SDCCD sign-off forms. Update In Design files with help from System Support Analyst (Final Proof--All changes must be made by 5:00 pm)
2021-11-22 | Mon | Student Systems Support Technician/Information Officers/Multimedia Specialist | Sys Support Analyst and Multimedia specialist provide reviewers with bluelines for final proofing.
2021-10-04 | Mon | Susan Topham, Vice Chancellor, Educational Services | Drop dead date to cancel printed schedule production
2021-08-30 | Mon | Systems Support Analyst | Send ISCLASS listings to Schedule Preparers
2018-08-24 | Fri | Systems Support Analyst and Schedule Preparers | Run Schedule Report from ISIS
2021-10-11 | Mon | TBD by each College | Deliver Changes to Off-Campus locations to Multimedia Specialist (City-Jeanie Tyler; Mesa-Arlis Svedberg; Miramar-Melanie Cordero)
2021-11-10 | Wed | Vice Presidents of Student Services | Email campus quantities needed to Jeff Mills, Systems Support Analyst.
Educational Services Division, District Office
| Vice Chancellor, Educational Services |  | Susan Topham
| Acting Dean, Educational Support Services |  | Krystal Henderson
| Dean, Online Instruction & Learning |  | Brian Weston
| Dean, Career Educaton & Workforce Development |  | Amertah Perman
| Dean, Instructional Services |  | Shelly Hess
| Systems Support Analyst, Educational Support Services |  | Jeff Mills
| Student Systems Support Technician, Student Services |  | Danya Sanchez
| Multimedia Specialist, Instructional Services |  | Eric Nunes
| Curriculum Analyst, Instructional Services |  | Erica Marrone
| Curriculum Technician, Instructional Services |  | Trila Gil
Communications and Public Relations, District Office
| District Graphic Artist |  | Claudia Azcona-Mercado
| Publications Editor & Supervisor |  | Leslie Hackett
District Sites (Colleges and CE Campuses)
| IT Production Control |  | District/Miramar
| Information Officers (PIOs) |  | Cesar Gumapas (City)
Jennifer Kearns (Mesa)
Stephen Quis (Miramar)
Ranessa Ashton (Continuing Education)
| Graphic Artists |  | Kim La Rue (City)
Hai Duong (Mesa)
Joan Mize (Miramar)
Luisa Davila (Continuing Education)
| Schedule Preparers |  | Kamini Bhakta (City)
Arlis Svedberg (Mesa)
Jennifer Ock and Melanie Cordero (Miramar)
Honors Coordinators
| District |  | Carmen Jay and Kirk Webley (Miramar)
| City |  | Kelly Mayhew and Hector Martinez
| Mesa |  | Ranmali Rodrigo and Rosiangela Escamilla
Off-site Printers
| Advantage, Inc. |  | Chris Baker, Mary Lytch
¹Production staff (i.e. district and non-district personnel involved in producing class schedules) will not be held accountable for meeting production timelines for information or alterations to the schedule, which are submitted after 5:00 PM on this date.
²We attempt to arrange schedule delivery by 10:00 AM and pick up by 2:00 PM; however this is subject to change depending on conditions at the time. Please contact Educational Services for more information.

## By Milestones
Major Milestones for Spring 2022
Dates | Description
2021-06-18 | Roll Forward Spring 2020 to Spring 2021
2021-08-20 | Student Services Changes
2021-10-18 | Final Download
2021-10-18 | Post CS Online Class Schedule
2021-10-25 | Student Services (1st Review)
2021-10-26 | Student Services 1st review due back to Instructional Services
2021-10-26 | PIOs First Page Proof
2021-11-01 | Page Proofs Delivered to Schedule Preparers/VPIs
2021-11-09 | Page Proofs Delivered to Multimedia Specialist
2021-11-15 | Review final page proofs
2021-11-22 | Proof Bluelines
2021-12-02 | Schedules Delivered
2021-12-06 | Open Registration